## Sheet1
ID | Milestone/ Deliverable | Task ID | WBS Task | Required Resources | Skills Required
1 | Project Planning and Research | 1.1 | Define Project Scope | Documentation Templates, Meeting Space | Project Management, Strategic Planning, Team Coordination
|  | 1.2 | Research & Feasibility Study | Internet access, Diy smart planter buiders community,Data on plant water needs | Research & Analysis, Data Interpretation, Industry Trends Understanding
|  | 1.3 | Develop Work Plan & Assignments | Microsoft Project, Collaboration Tool | Project Scheduling, Task Allocation, Risk Assessment
2 | Hardware Development | 2.1 | Design & Build Physical Structure | 3D Printer, PLA Filament, ABS Filament, Waterproof Sealant | CAD Design, 3D Printing
|  | 2.2 | Select & Integrate Sensors | Soil Moisture Sensors, Temp & Humidity Sensor, Light Sensor, Water Level Sensor | Electronics, Sensor Calibration
|  | 2.3 | Select & Integrate Pump | Water pump, Pump motor driver/ Relay Module, Tubing, Water Reservoir | System Design
|  | 2.4 | Circuit Design | ESP32, Breadboard, Jumper Wires, Soldering Kit, PCB Design Software (Optional) | PCB Layout Design (optional), Soldering, Circuit Debugging
|  | 2.5 | Design Power Supply | DC Power Supply circuit designs | Power Optimization, Basic Electronics
3 | Software Development | 3.1 | Mobile App/ Web App | REACT, Suitable IDE (Webstorm), Javascript | Mobile/ Web App development
|  | 3.2 | Implement Watering Control Logic | ESP32 Microcontroller, Moisture Threshold Algorithms, Pump driver Control Code | Arduino Programming, Algorithm Development, Microcontroller Programming
|  | 3.3 | Implement Manual Watering Option | Mobile App, Smartphone | Basic Electronics, Mobile App Integration, User Interface Design
|  | 3.4 | Implement Connectivity | ESP32, Blynk or MQTT Server (optional), Mobile App | Networking, IoT Protocols, Wireless Communication
4 | System Integration and Testing | 4.1 | Assemble Components | Soldering Kit, Screwdrivers, Waterproof Housing | Hands-on Assembly, Electrical Wiring
|  | 4.2 | Conduct Unit Testing | Multimeter,Test plan document | Electronics Testing, Debugging, Quality Control
|  | 4.3 | Perform Software-Hardware Integration | ESP32, Serial Monitor, Debugging Tools | Firmware Development, Hardware-Software Integration
|  | 4.4 | Field Testing with Real Plant | Potted Plant | Gardening, Soil Moisture Analysis
|  | 4.5 | Optimize Performance | Code Optimization Tools | Code optimization
5 | Deployment and Documentation | 5.1 | Final Assembly | Finished Components | Hands-on Assembly
|  | 5.2 | User Documentation | Technical Writing Software, Screen Recording Software | Technical Writing, Documentation, Video Editing
|  | 5.3 | Future Enhancements & Stretch Goals | Additional Features (Grow Lights, Fertilizer Control), AI Integration for Future Versions | AI/ML Fundamentals, Advanced IoT Systems, Growth Prediction Models